This Action Plan has been developed to deliver the recommendations outlined in the ‘Funding the Archives Sector’ research report (Sep 2012)

| 1 | Leadership |
| --- | --- |
| 1.1 | Develop stronger relationships at national and regional level with funders and stakeholders |
| 1.2 | Influence policy at national and local level to ensure sustainable funding for services |
| 1.3 | Support piloting of new approaches to funding and fundraising |
| 2 | Collaboration |
| 2.1 | Identify opportunities to bring together funders to enable greater strategic impact |
| 2.2 | Identify opportunities to bring together archive services to capitalise on funding initiatives |
| 3 | Good Practice |
| 3.1 | Provide mechanisms and opportunities for archive services to learn from each other |
| 3.2 | Ensure archive services have access to up-to-date and appropriate information on funding and fundraising |
| 4 | Advice |
| 4.1 | Ensure archive services have access to individual support where needed |
| 4.2 | Ensure funding support is part of all strategic discussions with archive services |
| 4.3 | Ensure archive services have access to appropriate training |

| Initiative | Timescale | Lead body and partners | Progress | Link to Report Rec. |
| --- | --- | --- | --- | --- |
| New initiatives (conditional on additional funding) |  |  |  |  |
| Set up a ‘development laboratory’ offering funding support for services to undertake pilots and disseminate lessons learnt | 2013-14 | TNA and partners tbd | Pending | 1.3 |
| New Initiatives using existing resources |  |  |  |  |
| Explore developing a body of national advocates for the sector from within the archive profession and beyond | 2013-14 | ARA, TNA | Pending | 1.2. |
| Undertake longitudinal research to map changes in funding of services | 2014-15 | TNA, UCL | Pending | 1.2 |
| Undertake further discussion and evidence gathering to consider whether to encourage archive services to join wider cultural sector crowd-funding platforms, or whether there is a need/opportunity to develop a sector-specific option | 2012-15 | TNA | Ongoing | 2.1 |
| Develop an online community of practice, similar to the Major Archives Project Learning Exchange (MAPLE) | 2012-13 | TNA | Pending | 3.1 |
| Undertake further research into the effectiveness of Friends’ groups as fundraising vehicles and disseminate the findings | 2013-14 | TNA | Pending | 3.1 |
| Encourage experienced practitioners to mentor less confident and/or experienced practitioners (linked to online community of practice) | 2013-15 | TNA | Pending | 3.1 |
| Provide introductory training for staff in the Archives Sector Development team to ensure they can support services | 2012-13 | TNA | Completed | 4.2 |
| Work closely with ACE regional teams to ensure appropriate support for combined museum/library/archive services within single cultural conversation | 2012-13 Ongoing | TNA, ACE | Ongoing | 4.2 |
| Ensure that sustainable funding is a key criteria for Archives Accreditation | 2012-13 Ongoing | TNA, CyMAL, NRS, PRONI | Ongoing | 4.2 |
| Identify training opportunities to improve confidence in financial planning, budget setting and accounting | 2013-14 | TNA, CyMAL | Pending | 4.3 |
| Existing/on-going work activity |  |  |  |  |
| Analyse status of current relationships with funders and develop improved engagement mechanisms | On-going | TNA | Ongoing | 1.1 |
| Use Archives for the 21st Century and evidence base to engage funders in discussion | On-going | TNA, CyMAL | Ongoing | 1.1. |
| Work with strategic and advocacy bodies in the wider cultural and heritage sectors (e.g. Heritage Alliance, BL, MA, Arts & Business (Business in the Community), NMDC, RLUK) to evidence need and support collaborative solutions | On-going | TNA | Ongoing | 1.1. |
| Use Archives for the 21st Century and evidence base to engage key stakeholders in discussions about delivering sustainable services | On-going | TNA, CyMAL | Ongoing | 1.2. |
| Continue to administer National Cataloguing Grants Scheme and work with partners to ensure the scheme’s long-term sustainability | 2012-14 | TNA, Pilgrim Trust and other trusts/foundations | Ongoing | 2.1 |
| Deliver school record digitisation project and evaluate lessons learnt | 2012-15 | ARA, TNA and archive services | Ongoing | 2.2 |
| Produce case studies tailored to illustrate the fundraising approaches identified in the report and keep these refreshed | 2012-13 Ongoing | TNA | Pending | 3.1 |
| Use The National Archives website as a primary destination for services seeking information on funding sources, techniques and guidance | 2012-13 Ongoing | TNA | Ongoing | 3.2 |
| Use The National Archives communication routes (e-updates, briefings etc.) to direct archive services to key relevant information | Ongoing | TNA | Ongoing | 3.2 |
| Use publications and events targeted at the archives sector to disseminate relevant funding information | Ongoing | TNA, ARA | Ongoing | 3.2 |
| Ensure archive services have a named contact at The National Archives to approach for advice and review draft applications to targeted funding sources | Ongoing | TNA | Ongoing | 4.1 |
| Produce guidance on implications of trust status for archive services | 2012-13 | TNA | Completed | 4.1 |
| Ensure archive services have access to licensing expertise | Ongoing | TNA | Ongoing | 4.1 |
| Work with partners (e.g. BL Preservation Advisory Service, CyMAL, ARA regional and special interest groups, and bodies such as the Religious Archives Group) to provide training to targeted organisations | Ongoing | TNA | Ongoing | 4.3 |
| Deliver tailored workshops for potential Heritage Lottery Fund applicants | Ongoing | TNA, HLF | Ongoing | 4.3 |
| Raise awareness of Higher Education funding sources within the sector | 2012-13 Ongoing | TNA | Pending | 4.3 |
| Acronyms ACE - Arts Council England ARA – Archives & Records Association CyMAL - Welsh Government Division, CyMAL: Museums Archives and Libraries Wales | HLF – Heritage Lottery Fund NRS – National Records of Scotland TNA - The National Archives PRONI – Public Record Office of Northern Ireland UCL – University College London |